## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
IAC Internship Program 2023 - Data Analyst - Project Schedule
|  | PROJECT START DATE | 2023-07-31
|  | Display Week Sr No | 1 | [10 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25
 | time axis 2023-07-31 to 2023-10-01
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2023-07-31 to 2023-10-01
1 |  | Project Overview |  |  |  |  | 2023-07-31 | 2023-08-29
1.1 | Week 1 |  | Project Onboarding | - |  | Nikita Girase | 2023-08-01 |  | 2023-08-01 | 1 | Completed | Task Finished | NA
1.2 | Week 1 |  | Study the problem | - |  | Nikita Girase | 2023-08-02 |  | 2023-08-02 | 2 | Completed | Task Finished | NA
1.3 | Week 1 |  | Understanding business problem | - |  | Nikita Girase | 2023-08-03 |  | 2023-08-03 | 3 | Completed | Task Finished | NA
1.4 | Week 1 |  | Identify business problem | - |  | Nikita Girase | 2023-08-04 |  | 2023-08-04 | 1 | Completed | Task Finished | NA
1.5 | Week 1 |  | Data collection for problem statement | - |  | Nikita Girase | 2023-08-05 |  | 2023-08-05 | 1 | Completed | Task Finished | NA
2 |  | Project Initiation |  |  |  |  | 2023-08-07 | 2023-08-19
2.1 | Week 2 |  | Filled a project charter | - |  | Nikita Girase | 2023-08-07 |  | 2023-08-08 | 2 | Completed | Task Finished | NA
2.2 | Week 2 |  | Requirement elicitation questionaire | - |  | Nikita Girase | 2023-08-09 |  | 2023-08-11 | 4 | Completed | Task Finished | NA
2.3 | Week 2 |  | Weekly meeting attended | - |  | Nikita Girase | 2023-08-12 |  | 2023-08-12 | 2 | Completed | Attended | NA
2.4 | Week 3 |  | SRS Document | - |  | Nikita Girase | 2023-08-14 |  | 2023-08-16 | 3 | Completed | Task Finished | NA
2.5 | Week 3 |  | Attended requirement elicitation | - |  | Nikita Girase | 2023-08-17 |  | 2023-08-17 | 2 | Completed | Attended | NA
2.6 | Week 3 |  | Weekly meeting attended | - |  | Nikita Girase | 2023-08-19 |  | 2023-08-19 | 2 | Completed | Attended | NA
3 |  | Project Planning |  |  |  |  | 2023-08-21 | 2023-09-02
3.1 | Week 4 |  | Work Breakdown Structure | - |  | Nikita Girase | 2023-08-21 |  | 2023-08-22 | 4 | Completed | Task Finished | NA
3.2 | week 4 |  | Identify Risks | - |  | Nikita Girase | 2023-08-23 |  | 2023-08-23 | 3 | Completed | Task Finished | NA
3.3 | week 4 |  | Assumptions | - |  | Nikita Girase | 2023-08-24 |  | 2023-08-24 | 3 | Completed | Task Finished | NA
3.4 | week 4 |  | Weekly meeting attended | - |  | Nikita Girase | 2023-08-26 |  | 2023-08-26 | 2 | Completed | Attended | NA
3.5 | week 5 |  | Project Scheduling | - |  | Nikita Girase | 2023-08-28 |  | 2023-08-30 | 2 | Completed | Task Finished | NA
3.6 | week 5 |  | Filled RAID log | - |  | Nikita Girase | 2023-08-31 |  | 2023-09-01 | 3 | Completed | Task Finished | NA
3.7 | week 5 |  | started filling Lesson learnt log | - |  | Nikita Girase | 2023-09-01 |  | 2023-09-02 | 2 | Completed | Task Finished | NA
3.8 | week 5 |  | Weekly meeting attended | - |  | Nikita Girase | 2023-09-02 |  | 2023-09-02 | 2 | Completed | Attended | NA
4 |  | Project Execution |  |  |  |  | 2023-09-02 | 2023-09-20
4.1 | Week 6 |  | Finalised Goal Metrices | - |  | Nikita Girase | 2023-09-04 |  | 2023-09-05 | 2 | Completed | Task Finished | NA
4.2 | Week 6 |  | Finaliszed expected deliverables | - |  | Nikita Girase | 2023-09-06 |  | 2023-09-07 | 2 | Completed | Task Finished
4.3 | Week 6 |  | Finalised resources | - |  | Nikita Girase | 2023-09-08 |  | 2023-09-08 | 1 | Completed | Task Finished
4.4 | Week 6 |  | Weekly meeting attended | - |  | Nikita Girase | 2023-09-09 |  | 2023-09-09 | 3 | Completed | Attended
4.5 | Week 6 |  | Started performing EDA | Data Cleaning and preparation |  | Nikita Girase | 2023-09-11 |  | 2023-09-11 | 2 | Completed | Task Finished
4.5.1 | Week 7 |  |  | Data Analysing |  | Nikita Girase | 2023-09-12 |  | 2023-09-12 | 2 | Completed | Task Finished
4.5.2 | Week 7 |  |  | Solving Problem statements |  | Nikita Girase | 2023-09-13 |  | 2023-09-14 | 3 | Completed | Task Finished
4.5.3 | Week 7 |  |  | Visualizations |  | Nikita Girase | 2023-09-15 |  | 2023-09-20 | 4 | Completed | Task Finished
5 |  | Project Closure |  |  |  |  | 2023-09-21 | 2023-09-29
5.1 | Week 8 |  | Power BI | - |  | Nikita Girase | 2023-09-21 |  | 2023-09-23 | 2 | Completed | Task Finished | NA
5.2 | Week 8 |  | Video | - |  | Nikita Girase | 2023-09-24 |  | 2023-09-25 | 1 | Completed | Task Finished
5.3 | Week 8 |  | Documentation | - |  | Nikita Girase | 2023-09-26 |  | 2023-09-28 | 1 | Completed | Task Finished
5.4 | Week 8 |  | Submission | - |  | Nikita Girase | 2023-09-28 |  | 2023-09-29 | 1 | Completed | Task Finished
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you

## Project Plan
PROJECT PLAN
DOCUMENT VERSION: 1.0
INTERN NAME | Nikita Girase
PROJECT NAME | Performance Analyzer
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | PowerBI, Video, WBS, Charter, SRS, Project plan and schedule, Lesson learnt, RAID log, Report
PROJECT SCOPE | Analysing details like GPA, experiences and courses
PROJECT START DATE | 2023-07-31
PROJECT END DATE | 2023-09-30
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem | Nikita Girase | 2023-08-01 | 2023-08-03 | 3 | COMPLETED
| 1.2 Data Overlook | Nikita Girase | 2023-08-04 | 2023-08-04 | 1 | COMPLETED
| 1.3 Create a project charter | Nikita Girase | 2023-08-07 | 2023-08-09 | 3 | COMPLETED
| 1.4 Requirement gathering | Nikita Girase | 2023-08-10 | 2023-08-15 | 4 | COMPLETED
2 Planning
| 2.1 Analysis of business process | Nikita Girase | 2023-08-16 | 2023-08-17 | 2 | COMPLETED
| 2.2 Roles and responsibilities | Nikita Girase | 2023-08-18 | 2023-08-18 | 1 | COMPLETED
| 2.3 Design | Nikita Girase | 2023-08-19 | 2023-08-21 | 2 | COMPLETED
| 2.4 Documentation | Nikita Girase | 2023-09-16 | 2023-09-28 | 13 | COMPLETED
3 Execution
| 3.1 Finalize Dashboard Tool | Nikita Girase | 2023-08-22 | 2023-08-22 | 1 | COMPLETED
| 3.2 Build | Nikita Girase | 2023-08-23 | 2023-09-15 | 24 | COMPLETED
| 3.2.1 Features | Nikita Girase | 2023-08-23 | 2023-08-25 | 3 | COMPLETED
ATS friendly application
Interns to gain insights
| Data Cleaning | Nikita Girase | 2023-08-26 | 2023-08-26 | 1 | COMPLETED
| Unique Students | Nikita Girase | 2023-08-27 | 2023-08-28 | 2 | COMPLETED
GPA
Distribution of students across different year
| Family Income | Nikita Girase | 2023-08-29 | 2023-08-30 | 2 | COMPLETED
Family income affects various aspects
| City | Nikita Girase | 2023-08-31 | 2023-08-31 | 1 | COMPLETED
Average GPA among different cities
| Search relationship | Nikita Girase | 2023-09-01 | 2023-09-02 | 2 | COMPLETED
Family Income
GPA
Python Programming
| Expected Salary | Nikita Girase | 2023-09-03 | 2023-09-05 | 3 | COMPLETED
Experience with python
GPA
Family Income
City
High or low salary
| Event | Nikita Girase | 2023-09-05 | 2023-09-08 | 3 | COMPLETED
Student Know from college
Event related to Data Science
Event trend attract more students
Specific field of study
Promotion Channel
Many data Science related courses
| Outliers | Nikita Girase | 2023-09-09 | 2023-09-09 | 1 | COMPLETED
Search amoung dataset
Applied on quantity column
Method used to find outlier
| Tool(Power BI) | Nikita Girase | 2023-09-10 | 2023-09-12 | 3 | COMPLETED
Dashboard
Various Plots
Calculus
Merge column and then apply
Better Option of Graph is used
| Leadership Skill | Nikita Girase | 2023-09-13 | 2023-09-14 | 2 | COMPLETED
Give higher GPA
Give better expectations in salary
| Graduating Students | Nikita Girase | 2023-09-15 | 2023-09-15 | 1 | COMPLETED
How many students till 2024
Colleges
| 3.3 Testing | Nikita Girase | 2023-09-15 | 2023-09-21 | 6 | COMPLETED
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure | Nikita Girase | 2023-09-29 | 2023-09-29 | 1 | COMPLETED